**Stamford parking garage repairs update:**

-The contractor installed a total of 92 new anti-slip stair treads in garage stair #6 the week of 6/17/19 – 6/21/19.  Additional miscellaneous stair nosing replacements in garage stair #1 and garage stair #4 were also completed in June.

-The contractor began roof-level repairs on 7/8/19, and is currently working in “Phase 2” (occupying approx. 30 spaces rooftop on level 5, and 30 spaces below rooftop on level 4).  Aerial of phasing plan is below.

-Phase 2 is projected to take 24 days to complete (anticipated completion date of 8/8/19).

-Summary of work activity occurring in Phase 2:

                -Partial depth concrete wash repairs

                -Shear connector repairs/re-welding

                -Full depth flange repairs and miscellaneous crack repairs

                -Control joints replacement

                -Application of topically applied penetrating corrosion inhibitor

                -Removal of tee joints and cove sealants

                -Application of epoxy healer/sealer, overlay system, and heavy duty waterproofing membrane

                -Placement of new tee and cove joint sealants

                -Traffic line striping

                -Epoxy injection to underside of deck

