## Slide 1: 2020 COVID19 UPDATES Maintenance of Way Division
Track, Structures, Stations & Facilities
Metro-North Railroad
June 4, 2020

## Slide 2
Major Track Outage Highlights
  GCT
    Track dept. cleaning the Lower Level while OOS
      Took 4 tracks at a time on the lower level to clean and tackle misc. track conditions (tie plates, block tie etc.) See slide 8
    Replaced 745/705 switchpoint and stock rail on Ladder T on a continuous outage
      Would have worked 1 extended, overnight shift but because LL is closed we can take it OOS and work over 3 days. See slide 8
  Mott Haven
    Tested all of MO territory with SRS129 in record time. See slide 7
      80% of territory could be done on days without night outages due to current schedule.
    Surfacing CP 5 See slide 6
      Hard outages to get due to exchange between Hudson and Harlem, we were able to take 20 hour windows to surface 13A, N24B, 45, 47 switches all surfaced last week
    Sandy Contractor (Trk 1 between CP 6 and CP 8, Trk 2 CP 10 to CP 11) and Harlem Express Contractor (Trk 2 CP 112 to CP 212 and Trk 3 inside CP 112) granted continuous outages that would have taken multiple weekends of force account support.

## Slide 3
Major Track Outage Highlights
  Hudson
    Rail jobs: 37 curve high and low side on both tracks 2 and 1 were completed by NY Projects, Scheduled for later in the year but completed now due to workforce reductions in MoW. See slide 5
    Sperry testing: Both POK and Harmon track will have their entire subdivision tested in record time – both a product of the current operating schedule and frequency of testing. See slide 7
    Built Cortlandt temporary platform much quicker and less track outages required. See slide 12
    Hudson Express cable contractor work continued with no impacts to schedule
  Harlem
    CP 119 Switch Renewal: not on original 2020 plan but pursued due to limited ridership and the ability to secure use of the Parking lot adjacent to CP 119; Outage was also taken continuous due to the operating schedule which drastically cut down on the expected duration
    HA 19.35 bridge timbers replacement. See slide 10
      This was an extra job that was not in the plan for 2020, would have been really tough and probably 4 weekends of work. Work completed in a 7 day period
    Harlem express cable CP 130 to CP 136: Planned as weekend and night work during 2020. Took it continuous instead due to the whole workforce reduction issues with Power/Signal
    Wassaic bridge work: Weekend service cancelled and no busses provided due to ridership. Track dept. replaced and surfaced a GEO hit on muddy river bridge

## Slide 4
Major Track Outage Highlights
  New Haven
    Springdale track welding inside CP 217 and CP 216 that would have been night work done during the day due to less trains and being able to single track
    Geometry condition on the crossover at CP 216, was a much easier fix with almost no Amtrak trains running and less time to fix was needed
    Trk 1 CP 217 to CP 223 removed from service for tie condition See slide 5
    Westport station – Utilized track 3 outage to cut and extend station platform See slide 11
    Springdale track record time to test subdivision with SRS129. Outside tracks included all on daytime hours. Operation was able to single track without bridge plates to expedite testing. See slide 7
    Branch outages: Planned for later in the year but taken now due to limited ridership. See slide 5
      Danbury Branch continuous outage for ties, crossing renewal, bridge timber replacement and cycle surfacing
      Waterbury Branch continuous outage for ties and Signal contractor
    Mudspot SMARTrack outage on track 2 between CP 266 and CP 271, will run railvac and CWPs out there to address multiple mudspots. See slide 5
    CP 234 46A and 46B switch replacement complete, moving on to the 68 and 810 switches. This outage would have again been very difficult operationally because it closes Stamford yard. Thus far, this 7 day outage continuous outage has removed 6 weekends of work with little impact to the operation. See slide 6

## Slide 5
Rail Replacement
Production Tie Replacement – 11,845 during COVID19
Production Mini Tie Replacement – May 2, 2020 – May 31, 2020
¤ Hudson, Trks 1 & 2 Curve 37 1.2 miles completed
¤ |  | Harlem |  | 423 | ties installed - Mt. Vernon West Yard
¤ |  | New Haven |  | 1,143 | ties installed - CP217 - CP223
 |  |  |  | 1,566 | Total ties installed
¤ |  | Danbury |  | 5,862 | ties installed - May 19 - Present
¤ |  | Waterbury |  | 7,300 | ties installed - April 13 - May 6
 |  |  |  | 13,617 | Total ties installed
Track Projects
Railvac-SmarTrack
¤ New Haven – Trk 2, CP266 – CP271 began vacuuming out debris and dirt in between ties.

## Slide 6
Switch Renewal – 7 switches installed during COVID19
Grade Crossing Renewal – 1 Installed During COVID19
¤ Harlem Line 1 crossing Jay St. Installed May 30th & 31st, 2020 and June 6th & 7th, 2020
Surfacing – 12.1 miles during COVID19
¤ |  | Hudson | 1.7 | miles
¤ |  | Harlem | 1.7 | miles
¤ |  | New Haven - NY | 0.2 | miles
¤ |  | New Haven - CT | 1.2 | miles
¤ |  | New Haven - WTBY | 5 | miles
¤ |  | New Haven - Danbury | 2.3 | miles
 |  |  | 12.1 | Total miles
¤ | New Haven | 46 A/B Switch Installed | 
¤ | WB | CP517, CP518, Beacon Falls Siding, CP500, CP502 | 

## Slide 7
Ultrasonic Rail Testing – 410 total miles during COVID19
Sperry Rail 129
    Sub 7 (NHL) March 16, 2020 – March 31, 2020
      Tested 47.0 miles
    Sub 6 (NHL, DB, NC) April 3, 2020 – April 24, 2020
      Tested 150.0 miles
    Sub 2 (HAR) May 4, 2020 – May 8, 2020
      Tested 49.0 miles
    Sub 3 (HUD) May 11, 2020 – Present
      Tested 97.0 miles
Sperry Rail 943
    Sub 4 (HUD) April 29, 2020 – May 13, 2020
      Tested 94.0 miles
    Sub 8 (PJL) May 18, 2020 – May 21, 2020
      Tested 90.0 miles

## Slide 8
  Track 15
    339 regular ties
    70 bracket ties
    409 total ties
    818 5 ½ inch Pandrol plates
    1,636 Pandrol Clips
    375 tons of new ballast
    3rd rail replaced the 3rd rail and will install new 3rd rail capping.
GCT Station Track Rehabilitation
GCT
    Track 102 – 106, Tracks 107-110, Track 111-114 – (In progress)
      Replace switchpoint and stock rail on Ladder T on a continuous outage, again would work 1 overnight shift but because LL is closed we can take it OOS and work over 3 days

## Slide 9
Structure Projects
  Accomplishments with the additional track outages that were granted during the Covid-19 crisis.
    Expedited HRLB Miter and Expansion Joint Installations. As part of that project, a total of 120 steel ties are being installed to replace existing timber ties and to support the new joint assemblies.
    During the last few weeks we have been able to obtain favorable continuous outages from OPS which has increased our ability to get work done. Within a one month period we will have installed the last remaining 41 steel ties that would normally have taken us 16 to 18 weekend outages (say 4 months) to complete.

## Slide 10
Harlem Line Deck Replacement Trk 1, MP 19.35
  Replace, Track 1 Bridge Timbers on the 100’ long through truss at HA19.35. completed week of May 25, 2020. Demobilization occurred May 30th and 31st, 2020
Crane
North Bay Timbers
Deck Replacement

## Slide 11
New Haven Line Westport Station
  Sawcut two feet of platform edge, installed new rebar and concrete and successfully corrected the platform edge gap conditions

## Slide 12
Hudson Line Cortlandt Station
  Installed platform to extend over to the track to board customers during extended track outages for other projects

## Slide 13
Drainage work
  (In progress) Performed ROW drainage improvements project south of Poughkeepsie Station between HU MP 73.22 (OH Mid-Hudson Highway) and MP 73.46 (OH Main Street).
  Pumped/removed water from ROW, cleaned ROW, spread stone, located drainage structures and opened-up drainage swales. Worked with Fred A. Cook to clean drainage ditches, catch basins and pipes.
  Performed ROW drainage improvements (re-establish existing swales) project to support Capital Department on the Port Jervis Line between MP JS 62.3 and MP JS 62.6.
  Worked with Fred A. Cook to clean catch basins, drainage pipes, and slot drains at Beacon Station parking lot (Hudson River side) to support Capital Department for future repaving.
  Inspected Hudson Line (MP 61 to MP 73) culvert inlets/outlets and cleared blockages where necessary.
  Cleaned the outlet of the culvert at HA MP 60.5 (Peckham Crossing) in support of Track Department high water concern.
  Removed debris accumulation at the inlet to the new drainage pipe at Dykemans crossing in Brewster, NY.
  Inspected/cleared Harlem Line recurring beaver dam obstructions.
  Inspected and cleared blockages from various Port Jervis Line culvert inlets/outlets.
  Removed beaver dam obstruction at inlet to culvert located at JS 47.28 (end of Bond Street, Central Valley, NY) in response to Trouble Ticket dated 5/21/2020.